Method Statement for Rigging and Flying Marc Brew in For Now I am

Written by: William Roper, Feb 2015

Location & Summary of work	Tramway Theatre Glasgow, then touring. / Installing system to lift and suspend Marc Brew by this ankles as part of a dance piece.
Time of work	TBC
Who will carry out the work. How long will it take.	William Roper an experienced aerial rigger. He is trained to carry out rescues, and has a work at height certificate and public liability insurance. / Up to three hours.
Description of the performance	Floor based dance piece, which culminates in Marc being lifted up by his ankles. Marc clips in to custom ankle cuffs. He is then lifted up. This will normally be done by a pulley system attached to a ground anchor or a counterweight system dependent on venue.
Load calculation.	Marc and his equipment weigh under 60kg (estimate) and her equipment. The potential dynamic factor is 2. / Therefore the maximum applied load on the anchor point will be: (60*2) = 120Kgf. / With a safety factor of 10:1 all equipment should have a minimum breaking strain of 1200kg (1.2Kn). Certain points are effected by pulleys splitting or increasing the load, see loading diagram for details.
Access techniques	Preferably a scissor lift, tallescope or similar. If necessary rope access techniques can be employed.
Public access to the working space.	It will be necessary to prevent members of the public from accessing the work space durign the rigging period.
Required preparation	Identify potential rigging points from plan, and gather appropriate loading information.
Equipment to be used	All rigging equipment will be supplied by William Roper and the performer. It will have been subject to regular checks by a competent person.
Order of operations	1. Ensure area is clear of obstacles and free from people workign below. / 2. Access beam / 3. Inspect beam for sound structure. / 4. Install points, and back up where appropriate. / 5.identify and install ground anchor.